## Assessment
Risk | Risk Statement | Response Strategy | Objective | Likelihood | Impact | Risk Level
Data Protection | The customer information is all stored on a maximum of three classes, with no separation and only minimal use of access modifiers | Separating out the customer information into separate classes, keeping the information all private, and ensuring the dependencies between classes were secure | Reduce the likelihood of personal information being shared outside of the database | Medium | Medium | High
Internet Connectivity | Much of the project access relies on connection to the internet, so that with poor connectivity comes a lack of access to the programme | Allowing the project to be pulled from the github repository means that, at least to some degree, the database can still be accessed | Access to database even under factors beyond the developer's control | Medium | Medium | Low
Developer Availability | As I was the only developer working on this particular project, if I am not available to work on this project then the database will go unedited | Adhering to health & safety guidelines, keeping the client informed of any extenuating circumstances | To ensure that Continuous Development is not delayed by something as trivial as a "sick day" | Medium | High | Medium
Workstation Functionality | If my workstation is not able to run all of the necessary files, as well as the testing elelments which do ultimately take up RAM, there may be a delay | QA has provided myself as a developer a workstation that, while primarily running on a different operating system, should be able to keep up with the workload | To ensure that the project and database is updated as often as possible and that work isn't lost | Low | High | Low
Public Access Github | With the database being made publicly available, this runs the risks of hackers taking advantage of your code and messing with your work | Either making the database private, or editing the user settings via github so that only those with a specific link can access the code | To ensure that the source code posted online is the one that is delivered and used by the client | Medium | High | High
Coding KnowHow | As I am new to java and code in general as a developer, I am not as experienced as other people who develop applications online | QA Consultants have chosen to be trainers, and their expertise is invaluable to those who attend QA Academy | To ensure that the code that is written is, ultimately, functional | High | High | Low
Time Management/ Stress/Burnout | If not carefully balanced, then I as a developer could end up feeling very stressed and overworked, losing myself to the code and feeling stuck | Remembering to take breaks for downtime, to get decent sleep, and to remain working at optimum levels | As above, to ensure that Continuous Integration is present during all stages of code development | High | Medium | Low

## Matrix
Risk | Likelihood | Impact | Risk Level
Data Protection
Internet Connectivity
Developer Availability
Workstation Functionality
Public Access Github
Coding KnowHow
Time Management
Key
High
Medium
Low